## Consolidated Productivity
CONSOLIDATED PRODUCTIVITY TABLE — Rev 1 — 02-Jul-26
Ref | Description | Unit | Rate / Day | BOQ Code | Activity Code | Source | Labour | Carpenter | Steel Fixer | Pipe Fitter | Mason | Electrician | Scaffolder | Grade Checker | Excavator | Shovel | Bob Cat | PTR | Paver | Roller | Baby Roller | Plate Compactor | Water Tanker | Grader | Crane | Spray Tanker | Piling Rig | Pile Cutting Machine | Dozer | TBM Machine | Shoring Machine | Notes / Flags
PART 1 — INFRASTRUCTURE & UTILITIES (Source: Productivity — governs where both sheets overlap)
General
1 | General Items |  | 1 DAY | GEN | GEN | P1 | 10
Mobilization
2 | Initial Mobilization |  | 1 DAY | GEN | IM | P1 | 15 | 2 |  |  | 2 | 1
3 | Establishment of offices for the Engineer's Staff |  | 1 DAY | GEN | ESF | P1 | 15 | 2 |  |  | 2 | 1
4 | Establishment of offices for the Contractor's Staff |  | 1 DAY | GEN | ECF | P1 | 15 | 2 |  |  | 2 | 1
5 | Erection of Project Sign Board |  | 1 DAY | GEN | SGB | P1 | 3
Sewer-Main line
6 | Excavation | m | 30 | SEW | EXC | P1 | 3 | [7 empty] | 1
7 | Formation preparation & Bedding | m | 30 | SEW | FRP | P1 | 1 | [13 empty] | 0.2 |  | 0.1
8 | Laying of Pipes | m | 30 | SEW | PL | P1 | 3 |  |  | 2
9 | Back Filling | m | 30 | SEW | BF | P1 | 3 | [8 empty] | 0.5 |  |  |  |  | 0.5 |  | 0.1
10 | Manhole | nr | 1 | SEW | MH | P1 | 2 | 2 | 2 |  | 1
11 | Fixing of Cover and Frame | nr | 2 | SEW | C&F | P1 | 0.5 |  |  |  | 0.5
12 | Testing- | m | 30 | SEW | TS | P1 | 2 |  |  | 0.5
13 | Construction of Sewerage Discharge Chamber | nr | 1 | SEW | CH | P1 | 8 | 4 | 4 |  | 4
Sewer -House Connection
14 | Excavation of House connection | m | 30 | SEW | HC.EXC | P1 | 2 | [7 empty] | 1
15 | Pipe Laying for house connection | m | 30 | SEW | HC.PL | P1 | 2 |  |  | 1
16 | Backfilling of house connection | m | 30 | SEW | HC.BF | P1 | 2 | [9 empty] | 0.5 |  |  |  | 0.5 |  | 0.1
17 | Fixing of House connection chambers | nr | 4 | SEW | HC.CH | P1 | 1 | 1 | 1 |  | 1
18 | Testing of house connection | m | 30 | SEW | HC.TS | P1 | 2 |  |  | 0.5
Stormwater Drainage-Mainline
19 | Dewatering Setup | m | 30 | SWD | DE | P1 | 2
20 | Excavation | m | 30 | SWD | EXC | P1 | 2 | [7 empty] | 1
21 | Formation preparation & Bedding | m | 30 | SWD | FRP | P1 | 1 | [13 empty] | 0.2 |  | 0.1
22 | Pipe Laying for Storm water | m | 30 | SWD | PL | P1 | 2 |  |  | 2
23 | Manhole / Catch basins (Fixing) | nr | 1 | SWD | MH/CB | P1 | 2 | 0.5 | 1 |  | 1
24 | Back Filling | m | 30 | SWD | BF | P1 | 2 | [8 empty] | 0.5 |  |  |  |  | 0.5 |  | 0.1
25 | Testing | m | 100 | SWD | TS | P1 | 2 |  |  | 0.5
26 | Fixing of Cover and Frame | nr | 2 | SWD | C&F | P1 | 0.5 |  |  |  | 0.5
27 | Fixing of Gullies | nr | 4 | SWD | GUL | P1 | 2 |  |  | 0.5 | 4 |  |  |  | 0.25 | 0.2 |  |  |  |  | 0.25 |  | 0.1
28 | Construction of over flow chamber | nr | 1 | SWD | CH | P1 | 4 | 2 | 2 |  | 2
Surface water Drainage-catch basin
29 | Excavation of Catchbasin & Pipe | m | 30 | SWD | CB.EXC | P1 | 1 | [7 empty] | 1
30 | Pipe Laying for Catchbasin | m | 30 | SWD | CB.PL | P1 | 1 |  |  | 1
31 | Fixing of Catchbasin | nr | 2.5 | SWD | CB-F | P1 | 1 | 0.5 |  |  | 0.5
32 | Backfilling of Catchbasin | m | 30 | SWD | CB-BF | P1 | 1 | [9 empty] | 0.5 |  |  |  | 0.5 |  | 0.2
33 | Testing of Catchbasin | m | 30 | SWD | CB-TS | P1 | 1 |  |  | 0.5
Fire Fighting
34 | Excavation | m | 60 | FF | EXC | P1 | 2 | [7 empty] | 1
35 | Formation preparation | m | 60 | FF | FRP | P1 | 1
36 | Pipe Laying | m | 60 | FF | PL | P1 | 2 |  |  | 1
37 | Construction of Distribution Chamber (Fixing) | nr | 0.5 | FF | CH | P1 | 2 | 1 |  |  | 0.5
38 | Valve Chamber with fittings(Fixing) | nr | 0.5 | FF | CH | P1 | 2 | 0.5 |  |  | 0.25
39 | Valve & fittings | nr | 0.5 | FF | VLV | P1 | 1 |  |  | 1
40 | Back Filling | m | 60 | FF | BF | P1 | 2 | [8 empty] | 0.5 |  |  |  |  | 0.5 |  | 0.1
41 | Testing | m | 40 | FF | TS | P1 | 2 |  |  | 0.5
Irrigation
42 | Excavation | m | 60 | IRR | EXC | P1 | 2 | [7 empty] | 1
43 | Formation preparation | m | 60 | IRR | FRP | P1 | 1
44 | Pipe Laying | m | 60 | IRR | PL | P1 | 2 |  |  | 1
45 | Construction of Distribution Chamber (Fixing) | nr | 0.5 | IRR | CH | P1 | 2 | 1 |  |  | 0.5
46 | Valve Chamber with fittings(Fixing) | nr | 0.5 | IRR | CH | P1 | 2 | 0.5 |  |  | 0.25
47 | Valve & fittings | nr | 0.5 | IRR | VLV | P1 | 1 |  |  | 1
48 | Back Filling | m | 60 | IRR | BF | P1 | 2 | [8 empty] | 0.5 |  |  |  |  | 0.5 |  | 0.1
49 | Testing | m | 40 | IRR | TS | P1 | 2 |  |  | 0.5
Potable Water
50 | Excavation | m | 32 | PW | EXC | P1 | 4 | [7 empty] | 1
51 | Formation preparation | m | 32 | PW | FRP | P1 | 5
52 | Pipe Laying | m | 72 | PW | PL | P1 | 5 |  |  | 1 | [14 empty] | 1
53 | Valve Chamber(Fixing) | nr | 2 | PW | CH | P1 | 2 | 0.5 |  |  | 0.25
54 | Valve Chamber(in situ) | nr | 0.07 | PW | CHI | P1 | 8 | 3 | 3 | 0.5 | 1 | [13 empty] | 0.25
55 | Valve (Fixing) | nr | 2 | PW | VLV | P1 | 2 |  |  | 1
56 | Construction of thrust blocks | nr | 2 | PW |  | P1 | 2 | 1 |  | 0.5 | 1
57 | Back Filling | m | 32 | PW | BF | P1 | 10 | [8 empty] | 1 | 0.5 |  |  |  | 1 |  | 0.1
58 | Testing | m | 500 | PW | TS | P1 | 8 |  |  | 4 |  | 1 | [10 empty] | 0.1
59 | House Connection | nr | 40 | PW | HC | P1 | 2 |  |  | 1 |  |  |  |  | 1 |  | 0.5 |  |  |  | 0.5 |  | 0.1
Telecom
60 | Excavation | m | 80 | TEL | EXC | P1 | 2 | [7 empty] | 1
61 | laying of Ducts | m | 80 | TEL | DUC | P1 | 2 |  |  | 1
62 | JRC Chambers | nr | 1 | TEL | CH | P1 | 2 |  |  |  | 1 | [13 empty] | 0.5
63 | Concrete Encasement | m | 20 | TEL |  | P1 | 2 | 2 | 1 |  | 0.25
64 | Backfilling | m | 80 | TEL | BF | P1 | 2 | [8 empty] | 0.5 |  |  |  |  | 0.5 |  | 0.1
65 | Testing | m | 80 | TEL | TS | P1 | 2 |  |  | 0.5
66 | Fixing of Chamber Covers | nr | 3 | TEL | C&F | P1 | 0.5 |  |  |  | 0.5
Street lighting
67 | Excavation | m | 60 | ST | EXC | P1 | 2 | [7 empty] | 1
68 | Street light duct and cable laying | m | 60 | ST | DUC-CBL | P1 | 2 |  |  | 1 |  | 1
69 | Street light Foundation(Fixing) | nr | 2 | ST | PFF | P1 | 2
70 | Feeder pillar/Chamber (Fixing) | nr | 2 | ST | FPC | P1 | 1 | 0.25 |  |  | 0.25 | 1
71 | Pole Fixing | nr | 3 | ST | PLF | P1 | 3 |  |  |  |  | 0.5 | [12 empty] | 0.5
72 | Cable Laying | m | 90 | ST | DUC-CBL | P1 | 2 |  |  |  |  | 0.5
73 | Backfilling | m | 60 | ST | BF | P1 | 2 | [9 empty] | 0.5 |  |  |  | 0.5 |  | 0.1
74 | Earthing system | m | 1 | ST | ES | P1 | 1 |  |  |  |  | 0.5
Electricity -HV/LV Cable
75 | Construction of Substation foundation | nr | 0.15 | Ele | SSF | P1 | 2 | 2 | 2 |  | 1 | [20 empty] | Activity code was #REF! in source; assigned SSF per Activity List usage — confirmed 02-Jul-26
Road Works- Carriageway
76 | Formation Preparation | m2 | 1000 | EW | FRP | P1 | 3 | [6 empty] | 1 | [5 empty] | 1 |  |  | 0.25 | 1
77 | Sub-base | m2 | 1000 | RW | SB | P1 | 3 | [6 empty] | 1 |  |  |  | 1 |  | 1 |  |  | 0.25 | 1
78 | Kerb stone | m | 75 | RW | KRB | P1 | 2 | 1 |  |  | 1 | [5 empty] | 0.5
79 | Gravel Road-base | m2 | 1500 | RW | RB | P1 | 3 | [9 empty] | 0.5 | 2 | 1 | 1 | 0.5
80 | Prime Coat | m2 | 3000 | RW | PC | P1 | 1 | [18 empty] | 1
81 | Tack Coat | m2 | 3000 | RW | TC | P1 | 1 | [18 empty] | 1
82 | Binder Course | m2 | 3000 | RW | BC | P1 | 10 | [10 empty] | 2 | 1 | 1 | 1
83 | Wearing Course | m2 | 3000 | RW | WC | P1 | 10 | [10 empty] | 2 | 1 | 1 | 1
84 | Laying of 80mm interlock tiles | m2 | 250 | RW | IL.80 | P1 | 4 |  |  |  | 2 | [5 empty] | 0.5 | [14 empty] | Unit corrected m3 → m2, confirmed by Nandakumar 02-Jul-26 (source read m3)
85 | 60mm interlock paving | m2 | 250 | RW | IL.60 | P1 | 4 |  |  |  | 2 | [5 empty] | 0.5
86 | Road Marking | m2 | 1000 | RW | RM | P1 | 3
87 | Traffic Signs | nr | 9 | RW | TS | P1 | 3
Earthwork
88 | Earthwork cutting & Filling | m3 | 2500 | EW | EWCF | P1 | 10 | [7 empty] | 1 | 1 | [12 empty] | 1
Pre-cast
89 | Pre-cast Sewer Manhole | nr | 0.5 | SEW | PC-MH | P1 | 3 | 3 | 3 |  | 1.5
90 | Pre-cast Storm water Manhole | nr | 0.6 | SWD | PC-MH | P1 | 3 | 3 | 3 |  | 1.5
91 | Pre-cast Sewer HC | nr | 5 | SEW | PC-HC | P1 | 2 | 2 |  |  | 1
92 | Pre-cast Catch basin | nr | 3 | SWD | PC-CB | P1 | 2 | 2 |  |  | 2
93 | Pre-cast Fire Fighting Valve Chamber | nr | 0.5 | FF | PC-CH | P1 | 2 | 2 | 2 |  | 1
94 | Pre-cast Irrigation Valve Chamber | nr | 0.5 | IRR | PC-CH | P1 | 2 | 2 | 2 |  | 1
95 | Pre-cast Potable Water Valve Chamber | nr | 0.5 | PW | PC-CH | P1 | 2 | 2 | 2 |  | 1
96 | Pre-cast JRC Chambers pre-cast | nr | 0.5 | TEL | PC-CH | P1 | 3 | 3 | 3
97 | Pre-cast Street Light Draw pit chamber | nr | 2 | ST | PC-DP | P1 | 2 | 1 | 1 |  | 1
98 | Pre-cast Street light Foundation | nr | 1.5 | ST | PC-SLF | P1 | 2 | 1 | 1 |  | 1
99 | Pre-cast Street light chamber | nr | 2 | ST | PC-CH | P1 | 1 | 1 | 1 |  | 1
100 | Pre-cast Street light feeder pillar | nr | 1 | ST | PC-FPF | P1 | 1 | 1 | 1 |  | 1
General Clearance,Breakout & remove pavement layer & kerbs,traffic signs & Trees
101 | General Clearance | m2 | 5000 | D&S | DMSC | P1 | 10 | [8 empty] | 1
102 | Breakout & remove pavement layer & kerbs,traffic signs & Trees | m2 | 5000 | D&S |  | P1 | 1 | [8 empty] | 1
103 | Remove existing Duct and Cables network | m | 100 | D&S |  | P1 | 2 | [7 empty] | 0.5
104 | Removal of Existing Street light pole foundation | nr | 20 | D&S |  | P1 | 1 | [8 empty] | 1
105 | Trial Trenches to locate the existing services | m3 | 100 | GI | TT | P1 | 20
106 | Bore holes and taking tests | nr | 5 | GI | BH | P1 | 0.4
107 | Remove existing trees | nr | 2 | D&S |  | P1 | 2 | [8 empty] | 0.5
108 | Removal of Kerbs | m | 500 | D&S |  | P1 | 5 | [8 empty] | 1
109 | Remove traffic signs | nr | 10 | D&S |  | P1 | 2
110 | Removal of signal posts | nr | 10 | D&S |  | P1 | 3 | [8 empty] | 0.5
111 | Demolish existing manholes/chambers | nr | 2 | D&S |  | P1 | 5 | [7 empty] | 0.5
112 | Removal of existing pipe work | m | 100 | D&S |  | P1 | 5 | [7 empty] | 0.5
Road Crossing Duct
113 | Excavation, Laying & Backfilling of Ducts | nr | 2 | ELE | RCD | P1 | 3 |  |  | 0.5 |  |  |  |  | 0.2 | [5 empty] | 0.25 |  | 0.1
114 | Excavation, Laying & Backfilling of Ducts | nr | 2 | ST | RCD | P1 | 3 |  |  | 0.5 |  |  |  |  | 0.2 | [5 empty] | 0.25 |  | 0.1
115 | Excavation, Laying & Backfilling of Ducts | nr | 2 | IRR | RCD | P1 | 3 |  |  | 0.5 |  |  |  |  | 0.2 | [5 empty] | 0.25 |  | 0.1
116 | Excavation, Laying & Backfilling of Ducts | nr | 2 | PW | RCD | P1 | 3 |  |  | 0.5 |  |  |  |  | 0.2 | [5 empty] | 0.25 |  | 0.1
MMR
117 | Setting Out-MMR (/P-1) |  |  | MMR | SET | P1 | 1
118 | Excavation for Foundation,Road base & Compaction-MMR (/P-1) |  |  | MMR | EXC | P1 | 1 | [7 empty] | 0.5
119 | Blinding for Foundation, Water Proofing & Screed-MMR (/P-1) |  |  | MMR | BLWP | P1 | 3 |  |  |  | 2
120 | Shuttering & Steel Fixing of Foundation-MMR (/P-1) |  |  | MMR | SH&SF.F | P1 | 2.67 | 1.33 | 1.33 |  | 1.33
121 | Casting of Foundation-MMR (/P-1) |  |  | MMR | F.CAST | P1 | 10 |  |  |  | 3
122 | Shuttering, Steel Fixing & Casting of Neck Column-MMR (/P-1) |  |  | MMR | SH&SF.N | P1 | 4 | 2 | 2 |  | 1
123 | Waterproofing for Foundation & Neck Column-MMR (/P-1) |  |  | MMR | WP.NC | P1 | 2
124 | Solid Block Under Tie Beams-MMR (/P-1) |  |  | MMR | SBUTB | P1 | 2 |  |  |  | 1
125 | Shuttering & Steel Fixing of Tie Beam-MMR (/P-1) |  |  | MMR | SH&SF.T | P1 | 4 | 2 | 2 |  | 1
126 | Casting of Tie Beam-MMR (/P-1)-STRUCTURE |  |  | MMR | TB.CAST | P1 | 10 |  |  |  | 2
127 | Waterproofing for Tie Beam-MMR (/P-1) |  |  | MMR | WP.TB | P1 | 2
128 | Backfilling up to Slab on Grade Level-MMR (/P-1) |  |  | MMR | BF | P1 | 2 | [8 empty] | 0.5 |  |  |  |  | 0.5 |  | 0.2
129 | Casting of Slab on Grade (Blinding, Water Proofing)-MMR (/P-1) |  |  | MMR | SLB.C-1 | P1 | 4 |  |  |  | 2
130 | Shuttering, Steel Fixing & Casting of Column-MMR (/P-1) |  |  | MMR | S&S.COL | P1 | 1.6 | 0.8 | 0.8 |  | 0.4
131 | Shuttering & Steel Fixing of Roof Slab and parapet-MMR (/P-1) |  |  | MMR | S&S.ROF | P1 | 3 | 2 |  | 2 | 2
132 | Casting of Roof Slab and parapet-MMR (/P-1) |  |  | MMR | SLB.C-2 | P1 | 10 |  |  |  | 3
133 | De-shuttering for Roof Slab-MMR (/P-1) |  |  | MMR | SLB.DS | P1 | 2 |  |  |  | 0.5
134 | Block Works-MMR (/P-1) |  |  | MMR | BW.ROOM | P1 | 4 |  |  |  | 2
135 | Internal & External Plastering-MMR (/P-1) |  |  | MMR | PLAST | P1 | 2 |  |  |  | 1
136 | Roof Water Proofing-MMR (/P-1) |  |  | MMR | WP.ROOF | P1 | 1
137 | Internal & External Painting-MMR (/P-1) |  |  | MMR | PAINT | P1 | 1
138 | Fixing of Doors & Windows-MMR (/P-1) |  |  | MMR | D&W | P1 | 2 | 1
139 | External Tiling Works & Ramp-MMR (/P-1) |  |  | MMR | TILE | P1 | 2 |  |  |  | 1
140 | Fixing of Canopy-MMR (/P-1) |  |  | MMR | CAN | P1 | 1 |  |  |  | 0.5
141 | Epoxy Flooring-MMR (/P-1) |  |  | MMR | EPOX | P1 | 2
142 | Final Coat Painting-MMR (/P-1) |  |  | MMR | FPAINT | P1 | 1
143 | MEP Conduits & DB's Enclosure-MMR (/P-1) |  |  | MMR | CONDUIT | P1 | 2 | 1
144 | Cable Tray,Cable Pulling & DB's dressing-MMR (/P-1) |  |  | MMR | CABLE | P1 | 1 |  |  |  |  | 1
145 | Laying of external coduits & Manhole work-MMR (/P-1) |  |  | MMR | MH&DUCT | P1 | 1 |  |  |  |  | 2
146 | Installing Split AC Unit. & MEP Final Fixes-MMR (/P-1) |  |  | MMR | AC | P1 | 1 |  |  |  |  | 2
147 | Excavation & Compaction-MMR (/P-1) |  |  | MMR | BW.EXC | P1 | 1 | [7 empty] | 1
148 | Blinding for Foundation-MMR (/P-1) |  |  | MMR | BW.FOUN | P1 | 4.5 |  |  |  | 3
149 | Waterproofing & Screed-MMR (/P-1) |  |  | MMR | BW.WP | P1 | 2
150 | Shuttering, Steel Fixing & Casting of Foundation-BW-MMR (/P-1) |  |  | MMR | BW.SC.F | P1 | 2 | 1 | 1 |  | 1
151 | Shuttering, Steel Fixing & Casting of Neck Column-BW-MMR (/P-1) |  |  | MMR | BW.SC.N | P1 | 2.67 | 1.33 | 1.33 |  | 0.67
152 | Solid Block Work-MMR (/P-1) |  |  | MMR | BW.TB.B | P1 | 2.67 |  |  |  | 1.33
153 | Waterproofing for Neck Column & Solid Block Works-MMR (/P-1) |  |  | MMR | BW.NC.W | P1 | 4 |  |  |  | 2
154 | Backfilling up to Tie Beam-MMR (/P-1) |  |  | MMR | BW.BF | P1 | 1 | [8 empty] | 0.5
155 | Shuttering & Steel Fixing of Tie Beam-MMR (/P-1) |  |  | MMR | BW.SF.B | P1 | 4 | 2 | 2 |  | 1
156 | Shuttering,Steel Fixing & Casting of Columns-MMR (/P-1) |  |  | MMR | BW.SC.C | P1 | 2 | 1 | 1 |  | 0.5
157 | Casting of Tie Beam-MMR (/P-1) BOUNDARY WALL |  |  | MMR | BW.TB.C | P1 | 10 |  |  |  | 3
158 | Block Works for Boundary Wall-MMR (/P-1) |  |  | MMR | BW.BLOC | P1 | 4.8 |  |  |  | 2.4
159 | Shuttering,Steel Fixing & Casting of Coping Beam-MMR (/P-1) |  |  | MMR | BW.C.CB | P1 | 4 | 2 | 2 |  | 2
160 | Plastering-MMR (/P-1) |  |  | MMR | BW.PLAS | P1 | 2 |  |  |  | 1
161 | Painting-MMR (/P-1) |  |  | MMR | BW.PAIN | P1 | 1
162 | Fixing of Gate-MMR (/P-1) |  |  | MMR | GATE | P1 | 2 |  |  |  | 1
Pit Works
163 | Box Shoring for Pit | Pit | 0.25 | PIT | SH-PIT | P1 | 15 | 2 |  | 2 | 1 |  |  |  | 1 | [7 empty] | 0.25
164 | Dewatering Setup | pit | 0.14 | PIT | DE-W | P1 | 4 |  |  | 1 |  | 1
165 | Excavation of pit | m3 | 300 | PIT | EX-PIT | P1 | 8 | [7 empty] | 1 | [9 empty] | 1
166 | Backfilling of Pit | layers | 4 | PIT | BF-PIT | P1 | 3 | [13 empty] | 1 |  | 0.25
167 | Reinstatement of Exiting Services / Pavement | pit | 0.14 | PIT | RES | P1 | 2
NDRC Machine Moblization/Demoblization
168 | Mobilization of Driving Machine | No. | 0.15 | NDRC | MO-D | P1 | 6 | 2 | 1 | 1 | 1 | 0.25 | [10 empty] | 1 |  | 0.1
169 | Re-setup Driving Machine | No. | 0.15 | NDRC | MO-RS | P1 | 6 | 2 | 1 | 1 | 1 | 1 |  |  | 1 | [7 empty] | 1 |  | 1
170 | Demobilization of Driving Machine | No. | 0.3 | NDRC | DMO-D | P1 | 6 | 2 | 1 | 1 | 1 | 0.25 |  |  | 1 | [7 empty] | 1 |  | 0.1
Driving Pipe from Pit
171 | Driving of Pipe from Pit | m | 3 | NDRC | DP | P1 | 6 |  |  |  |  | 1 | [17 empty] | 1
172 | Grouting of Pipe |  |  | NDRC | GT-PP | P1 | 6 |  |  |  | 2
173 | Testing of Pipe |  |  | NDRC | TT-PP | P1 | 3
174 | Connection to Existing Network |  |  | NDRC | CONN | P1 | 10 |  |  | 2
Adjust Level of Existing Manholes
175 | Adjust Level of Existing Manholes | nr | 2 | LEV |  | P1 | 2 | [22 empty] | 1
PART 2 — STRUCTURES & P2-UNIQUE SERVICES (Source: Productivity 2 — Skilled Labour merged into Labour)
Element / Service: Pile
P01 | Piling 1200Ø bored | piles | 1 |  | PL-1200 | P2 | 4 | [19 empty] | 1
P02 | Piling 1500Ø bored | piles | 1 |  | PL-1500 | P2 | 4 | [19 empty] | 1
P03 | Pile Excavation | mob | 0.5 |  | PL-EX | P2 | 2 | [7 empty] | 1
P04 | Pile Cutting & Preparation | piles | 5 |  | PL-PLC | P2 | 4 |  |  |  | 2 | [16 empty] | 1
Element / Service: PC
P05 | Blinding Concrete | m² | 25 |  | PC-BL | P2 | 2 |  |  |  | 2
P06 | Pile Cap Reinforcement | t | 1.4 |  | PC-REF | P2 | 4 |  | 4
P07 | Pile Cap Formwork | m² | 144 |  | PC-FW | P2 | 4 | 6
P08 | Pile Cap Concrete | m³ | 50 |  | PC-CON | P2 | 4 |  |  |  | 2
P09 | Pile Cap Curing | FIXED days | 1 |  | PC-CUR | P2 | 1
P10 | Pile Cap FW Removal | m² | 70 |  | PC-FWR | P2 | 4 | 1
P11 | Pile Cap Waterproofing | m² | 50 |  | PC-WP | P2 | 4 | [24 empty] | Skilled Labour (2) merged into Labour per instruction 02-Jul-26
P12 | Pile Cap Backfilling | m³ | 100 |  | PC-BF | P2 | 6 | [8 empty] | 0.5 |  |  |  |  | 1 |  | 0.2
Element / Service: Pier
P13 | Pier Scaffolding | m³ | 50 |  | PR-SCF | P2 | 4 | [5 empty] | 2
P14 | Pier Column Reinforcement | t | 1 |  | PR-REF | P2 | 4 |  | 4
P15 | Pier Column Formwork | m² | 48 |  | PR-FW | P2 | 4 | 6
P16 | Pier Column Concrete | m³ | 35 |  | PR-CON | P2 | 4 |  |  |  | 1
P17 | Pier Column FW Removal | m² | 70 |  | PR-FWR | P2 | 4 | 1
P18 | Pier Head Reinforcement | t | 1.5 |  | PH-REF | P2 | 4 |  | 6
P19 | Pier Head Formwork | m² | 48 |  | PH-FW | P2 | 4 | 6 |  |  |  |  | 2
P20 | Pier Head Concrete | m³ | 45 |  | PH-CON | P2 | 4 |  |  |  | 1
P21 | Pier Head FW Removal | m² | 60 |  | PH-FWR | P2 | 4 | 1
Element / Service: BE
P22 | Bearing Installation | bearings | 4 |  | BE-BER | P2 | 6 |  |  |  | 2 | [20 empty] | Skilled Labour (4) merged into Labour per instruction 02-Jul-26
Element / Service: PE
P23.a | Pile Extension Scaffolding | nr | 2 |  | PE-SCF | P2 | 4 | [5 empty] | 2
P23 | Pile Extension Reinforcement | t | 0.75 |  | PE-REF | P2 | 4 |  | 3
P24 | Pile Extension Formwork | m² | 60 |  | PE-FW | P2 | 4 | 5
P25 | Pile Extension Concrete | m³ | 28 |  | PE-CON | P2 | 4 |  |  |  | 1
P26 | Pile Extension Curing | FIXED days | 1 |  | PE-CUR | P2 | 1
P27 | Pile Extension FW Removal | m² | 55 |  | PE-FWR | P2 | 4 | 1
P28 | Pile Extension Waterproofing | m² | 50 |  | PE-WP | P2 | 4 | [24 empty] | Skilled Labour (2) merged into Labour per instruction 02-Jul-26
P29 | Pile Extension Backfilling | m³ | 75 |  | PE-BF | P2 | 6
Element / Service: HB
P30 | Header Beam Scaffolding | m³ | 75 |  | HB-SCF | P2 | 4 | [5 empty] | 3
P31 | Header Beam Formwork | m² | 72 |  | HB-FW | P2 | 4 | 6
P32 | Header Beam Reinforcement | t | 1.4 |  | HB-REF | P2 | 4 |  | 4
P33 | Header Beam Concrete | m³ | 35 |  | HB-CON | P2 | 4 |  |  |  | 2
P34 | Header Beam Curing | FIXED days | 1 |  | HB-CUR | P2 | 1
P35 | Header Beam FW Removal | m² | 70 |  | HB-FWR | P2 | 4 | 1
Element / Service: DS
P36 | Deck Scaffolding / Falsework | m³ | 150 |  | DS-SCF | P2 | 6 | [5 empty] | 6
P37 | Bottom Slab Formwork | m² | 192 |  | DS-FW.B | P2 | 4 | 8
P38 | Bottom Slab + Web Reinforcement | t | 3.5 |  | DS-REF.B | P2 | 4 |  | 10
P39 | Tendon Duct Installation | m | 55 |  | DS-TDT | P2 | 8 |  |  | 2 | [21 empty] | Skilled Labour (6) merged into Labour per instruction 02-Jul-26
P40 | Bottom Slab Concrete | m³ | 80 |  | DS-CON.B | P2 | 6 |  |  |  | 6
P41 | Kicker Preparation | LM | 28 |  | DS-KR | P2 | 4 | 2 | 1 |  | 2
P42 | Web Formwork | m² | 96 |  | DS-FW.W | P2 | 4 | 8
P43 | Web Concrete | m³ | 45 |  | DS-CON.W | P2 | 4 |  |  |  | 2
P44 | Web FW Removal | m² | 90 |  | DS-FWR.W | P2 | 4 | 1
P45 | Top Slab Formwork | m² | 192 |  | DS-FW.T | P2 | 4 | 8
P46 | Top Slab Reinforcement | t | 3.5 |  | DS-REF.T | P2 | 4 |  | 10
P47 | Top Slab Concrete | m³ | 65 |  | DS-CON.T | P2 | 6 |  |  |  | 4
P48 | Deck Curing | FIXED days | 1 |  | DS-CUR | P2 | 1
P49 | Formwork Striking | m² | 150 |  | DS-FWR.S | P2 | 6 | 2 |  |  |  |  | 4
Element / Service: PT
P50 | PT Stressing | tendons | 3 |  | PT-STR | P2 | 6 | [24 empty] | Skilled Labour (4) merged into Labour per instruction 02-Jul-26
P51 | PT Grouting | tendons | 6 |  | PT-GRT | P2 | 6 | [24 empty] | Skilled Labour (4) merged into Labour per instruction 02-Jul-26
Element / Service: BW
P53 | Backwall Reinforcement | t | 1 |  | BW-REF | P2 | 4 |  | 4
P54 | Backwall Formwork | m² | 60 |  | BW-FW | P2 | 3 | 5
P55 | Backwall Concrete | m³ | 18 |  | BW-CON | P2 | 4 |  |  |  | 1
P56 | Backwall FW Removal | m² | 55 |  | BW-FWR | P2 | 4 | 1
P56.a | Backwall Waterproofing | m² | 50 |  | BW-WP | P2 | 4 | [24 empty] | Skilled Labour (2) merged into Labour per instruction 02-Jul-26
P56.b | Backwall Curing | FIXED days | 1 |  | BW-CUR | P2 | 1
Element / Service: EJ
P57 | Expansion Joint Installation | m | 4 |  | EJ-EXJ | P2 | 6 |  |  |  | 2 | [20 empty] | Skilled Labour (4) merged into Labour per instruction 02-Jul-26
Element / Service: AS
P58.a | Approach Slab Blinding | m² | 25 |  | AS-BL | P2 | 2 |  |  |  | 2
P58 | Approach Slab Reinforcement | t | 1.4 |  | AS-REF | P2 | 4 |  | 4
P59 | Approach Slab Formwork | m² | 120 |  | AS-FW | P2 | 3 | 5
P60 | Approach Slab Concrete | m³ | 45 |  | AS-CON | P2 | 4 |  |  |  | 2
P61 | Approach Slab FW Removal | m² | 70 |  | AS-FWR | P2 | 4 | 1
Element / Service: Gan
P62 | Installation of Gantry | nr | 70 |  | GAN | P2 | 8 | [17 empty] | 1 | [6 empty] | Skilled Labour (4) merged into Labour per instruction 02-Jul-26
Element / Service: FW
P63 | Finishing Works |  | 10 |  | BR-FW | P2 | 4 | 4 | 4 |  | 4 | [20 empty] | Unit missing in source — GAP, confirm
Element / Service: MSE
P64 | Foundation / Levelling Pad | m | 30 |  | MSE-FND | P2 | 6 | [7 empty] | 1
P66 | Strip Laying (all lifts) | strips | 96 |  | MSE-STRP | P2 | 4
P67 | Select Backfill Place & Compact | m3 | 350 |  | MSE-BF | P2 | 4 | [8 empty] | 1 |  |  |  | 1 | 2 | 2 | 0.25
P68 | Coping Beam / Capping | m | 15 |  | MSE-COP | P2 | 4 | 2 | 2
Element / Service: BASE SLAB
P69 | Formation Preparation |  | 1000 |  | CUL-FP | P2 | 3 | [24 empty] | Unit missing in source — GAP, confirm
P70 | Blinding Concrete |  | 600 |  | CUL-BL | P2 | 4 |  |  |  | 2 | [20 empty] | Unit missing in source — GAP, confirm
P71 | 2-ply waterproofing membrane (Bottom slab) |  | 200 |  | CUL-WPM | P2 | 6 |  |  |  | 3 | [20 empty] | Unit missing in source — GAP, confirm
P72 | 50mm screed on bottom slab |  | 600 |  | CUL-SCR | P2 | 3 | [8 empty] | 1 | [15 empty] | Unit missing in source — GAP, confirm
P73 | Steel fixing-Bottom slab | tonn | 2 |  | CUL-SF-BS | P2 | 3 |  | 5 | [15 empty] | 0.25
P74 | Formwork-Bottom slab | m2 | 75 |  | CUL-FW-BS | P2 | 2 | 5 | [16 empty] | 0.25
P75 | Concrete-Bottom slab | m3 | 750 |  | CUL-CON-BS | P2 | 2 |  |  |  | 2
Element / Service: WALL
P76 | Wall Steel fixing |  | 2.8 |  | CUL-SF-W | P2 | 3 |  | 7 | [15 empty] | 0.25 | [6 empty] | Unit missing in source — GAP, confirm
P77 | Wall form work |  | 40 |  | CUL-FW-W | P2 | 2 | 5 | [16 empty] | 0.25 | [6 empty] | Unit missing in source — GAP, confirm
P78 | Wall Concrete | m3 | 750 |  | CUL-CON-W | P2 | 2 |  |  |  | 2
P79 | Wall Formwork removal |  | 80 |  | CUL-FWR-W | P2 | 1 | 1 | [16 empty] | 0.25 | [6 empty] | Unit missing in source — GAP, confirm
P80 | Waterproofing wall out side |  | 200 |  | CUL-WP-W | P2 | 6 |  |  |  | 3 | [20 empty] | Unit missing in source — GAP, confirm
P81 | Filling around out side wall |  | 150 |  | CUL-FILL-W | P2 | 3 | [13 empty] | 1 |  | 0.25 | [8 empty] | Unit missing in source — GAP, confirm
Element / Service: TOP SLAB
P82 | Scaffolding for top slab |  | 45 |  | CUL-SCF-TS | P2 | 1 | 1 |  |  |  |  | 1 | [11 empty] | 0.25 | [6 empty] | Unit missing in source — GAP, confirm
P83 | Formwork for top slab |  | 45 |  | CUL-FW-TS | P2 | 2 | 2 |  |  |  |  | 2 | [11 empty] | 0.25 | [6 empty] | Unit missing in source — GAP, confirm
P84 | Steel fixing for top slab |  | 1 |  | CUL-SF-TS | P2 | 2 |  | 5 | [15 empty] | 0.25 | [6 empty] | Unit missing in source — GAP, confirm
P85 | Concrete-Top slab |  | 500 |  | CUL-CON-TS | P2 | 2 |  |  |  | 2 | [20 empty] | Unit missing in source — GAP, confirm
P86 | Removal of formwork & scaffolding |  | 150 |  | CUL-FWR-TS | P2 | 1 | 1 | [16 empty] | 0.25 | [6 empty] | Unit missing in source — GAP, confirm
P87 | Curing |  | 1 |  | CUL-CUR-TS | P2 | 1 | [24 empty] | Unit missing in source — GAP, confirm
P88 | Waterpoofing above top slab |  | 200 |  | CUL-WP-TS | P2 | 6 |  |  |  | 3 | [20 empty] | Unit missing in source — GAP, confirm
P89 | MSE wall & filling above top slab |  | 500 |  | CUL-MSE-TS | P2 | 2 | [8 empty] | 0.5 | [15 empty] | Unit missing in source — GAP, confirm
Element / Service: APP SLAB
P90 | Blinding Concrete |  | 600 |  | CUL-BL-AS | P2 | 4 |  |  |  | 2 | [20 empty] | Unit missing in source — GAP, confirm
Element / Service: Finishing Works
P91 | Mass Concrete-bass slab |  | 600 |  | CUL-MC | P2 | 2 |  |  |  | 2 |  |  |  |  | 0.5 | [6 empty] | 0.2 | [8 empty] | Unit missing in source — GAP, confirm
P92 | Kerbstone-Inside culvert |  | 75 |  | CUL-KB | P2 | 2 | 1 |  |  | 1 | [20 empty] | Unit missing in source — GAP, confirm
P93 | Side walk-inside culvert |  | 250 |  | CUL-SW | P2 | 4 | 1 |  |  | 2 | [20 empty] | Unit missing in source — GAP, confirm
P94 | Finishing layer |  | 100 |  | CUL-FL | P2 | 2 | [24 empty] | Unit missing in source — GAP, confirm
Element / Service: Survey
P106 | Survey & Setting Out | m | 100 |  | SSO | P2 | 3 | [24 empty] | Skilled Labour (1) merged into Labour per instruction 02-Jul-26
Element / Service: Pile
P107 | Test Piling | pile | 1 |  | TP | P2 | 6 | [19 empty] | 1
Element / Service: Precast
P108 | Precast MSE Panel Erection | panels | 15 |  | PRC-MSE | P2 | 4 | [17 empty] | 1 | [6 empty] | GOVERNS MSE panel erection: 15 panels/day per Nandakumar 02-Jul-26. P65 MSE-PAN 24/day and P1 20 m2/day superseded — see Conflict Register
Element / Service: RCD
P116 | Road Crossing Duct - Storm Water | nr | 1 |  | RCD-SW | P2 | 6 | [7 empty] | 0.25 | [5 empty] | 0.25
P119 | Road Crossing Duct - Natural Gas | nr | 1 |  | RCD-GAS | P2 | 6 | [7 empty] | 0.25 | [5 empty] | 0.25
P120 | Road Crossing Duct - Etisalat | nr | 1 |  | RCD-ETI | P2 | 6 | [7 empty] | 0.25 | [5 empty] | 0.25
P121 | Road Crossing Duct - Du/Fibre/SEWA/Sewer | nr | 1 |  | RCD-DU | P2 | 6 | [7 empty] | 0.25 | [5 empty] | 0.25
Element / Service: Potable Water
P139 | Potable Water - Excavation & Laying | m | 30 |  | UT-PW-EXC | P2 | 6 |  |  | 1 |  |  |  |  | 1 | [16 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
P140 | Potable Water - Shutdown & Connection | nr | 1 |  | UT-PW-CON | P2 | 4 |  |  | 2 | [21 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
P141 | Potable Water - Removal of Existing | m | 50 |  | UT-PW-REM | P2 | 4 | [7 empty] | 1 | [16 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
P142 | Potable Water - Backfilling | m | 50 |  | UT-PW-BF | P2 | 4 | [8 empty] | 0.5 |  |  |  |  | 0.5 |  | 0.25 | [8 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
P143 | Potable Water - Protection Slab | m | 50 |  | UT-PW-PS | P2 | 4 |  | 1 | [22 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
Element / Service: Etisalat
P146 | Etisalat - Excavation & Duct Laying | m | 30 |  | UT-ETI-EXC | P2 | 6 | [7 empty] | 1 | [16 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
P147 | Etisalat - Cable Laying & Connection | m | 50 |  | UT-ETI-CL | P2 | 4 |  |  |  |  | 1 | [19 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
P148 | Etisalat - Removal of Existing | m | 50 |  | UT-ETI-REM | P2 | 4 | [7 empty] | 1 | [16 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
P149 | Etisalat - Backfilling | m | 50 |  | UT-ETI-BF | P2 | 4 | [8 empty] | 0.5 |  |  |  |  | 0.5 |  | 0.25 | [8 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
P150 | Etisalat - Protection Slab | m | 50 |  | UT-ETI-PS | P2 | 4 |  | 1 | [22 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
Element / Service: Natural Gas
P152 | Natural Gas - Excavation & Laying | m | 30 |  | UT-GAS-EXC | P2 | 4 |  |  | 1 |  |  |  |  | 1 | [16 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
P153 | Natural Gas - Shutdown & Connection | nr | 1 |  | UT-GAS-CON | P2 | 4 |  |  | 2 | [21 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
P154 | Natural Gas - Removal of Existing | m | 50 |  | UT-GAS-REM | P2 | 4 | [7 empty] | 1 | [16 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
P155 | Natural Gas - Backfilling | m | 50 |  | UT-GAS-BF | P2 | 4 | [8 empty] | 0.5 |  |  |  |  | 0.5 |  | 0.25 | [8 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
P156 | Natural Gas - Protection Slab | m | 50 |  | UT-GAS-PS | P2 | 4 |  | 1 | [22 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
P157 | Natural Gas - Culvert Construction | m | 5 |  | UT-GAS-CUL | P2 | 6 | 2 | 2 | [5 empty] | 1 | [16 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
Element / Service: TSE
P159 | TSE - Diversions | m | 30 |  | UT-TSE | P2 | 4 |  |  | 1 |  |  |  |  | 1 | [16 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
Element / Service: Irrigation
P160 | Irrigation - Removal/Relocation | nr | 1 |  | UT-IRR | P2 | 4 | [7 empty] | 0.5 | [16 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
Element / Service: Storm Water
P161 | Storm Water Relocation - Excavation & Laying | m | 20 |  | UT-SW-EXC | P2 | 6 |  |  | 1 |  |  |  |  | 0.5 | [16 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
P162 | Storm Water Relocation - Shutdown & Connection | nr | 50 |  | UT-SW-CON | P2 | 4 |  |  | 2 | [21 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
P163 | Storm Water Relocation - Removal | m | 30 |  | UT-SW-REM | P2 | 4 | [7 empty] | 0.5 | [16 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
P164 | Storm Water Relocation - Backfilling | m | 50 |  | UT-SW-BF | P2 | 4 | [8 empty] | 0.5 |  |  |  |  | 0.5 |  | 0.25 | [8 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
Element / Service: Electrical
P166 | SEWA 132KV HV Cable - Protection | nr | 1 |  | UT-HV | P2 | 6 |  |  |  |  | 2 |  |  | 1 | [16 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
P167 | SEWA LV Cable - Diversion | nr | 1 |  | UT-LV | P2 | 4 |  |  |  |  | 1 |  |  | 1 | [16 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
Element / Service: Telecom
P168 | Fibre-Optic Cable - Protection | nr | 1 |  | UT-FOC | P2 | 4 |  |  |  |  | 1 |  |  | 1 | [16 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
P169 | Du Telecom - Protection | nr | 1 |  | UT-DU | P2 | 4 |  |  |  |  | 1 |  |  | 1 | [16 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
Element / Service: General
P170 | Traffic Diversion - Setup | ls | 1 |  | TD | P2 | 6
P176 | Utility Protection | ls | 1 |  | UT-PROT | P2 | 4 | [24 empty] | Relocation/protection of existing services — distinct from P1 new-works rates (confirmed 02-Jul-26)
Element / Service: Road Works
P177 | Road Works - Traffic Diversion | m² | 1000 |  | RW-TD | P2 | 4
P178 | Guardrail / Crash Barrier Installation | m | 50 |  | RW-GR | P2 | 6 | [17 empty] | 1

## Assumptions & Decisions
ASSUMPTIONS & DECISIONS REGISTER — Rev 1 — 02-Jul-26
# | Item | Basis
1 | Conflict rule (Rev 1): P1 governs ALL conflicted services in the Conflict Register. Sole exception: MSE panel erection = P2 15 panels/day (P108). Elsewhere P2 governs structures / P2-unique services only. | Per Nandakumar instruction, 02-Jul-26. Superseded rates retained in Conflict Register — nothing deleted.
2 | Skilled Labour column removed; counts merged into general Labour. Affected rows carry an inline flag. | Confirmed by Nandakumar, 02-Jul-26.
3 | P2 'Steel Roller' merged with P1 'Roller' as one equipment type 'Roller'. | Confirmed by Nandakumar, 02-Jul-26.
4 | P2 'Pile rig' merged with P1 'Pilling Rig' as 'Piling Rig'. | Confirmed by Nandakumar, 02-Jul-26.
5 | P2 rows with no unit in source flagged 'Unit missing — GAP'. No units invented. | Gap rule.
6 | P1 'Laying of 80mm interlock tiles' unit corrected m3 → m2 (source read m3). | Confirmed m2 by Nandakumar, 02-Jul-26.
7 | P1 Substation foundation activity code was #REF!; assigned 'SSF' to match Activity List usage. | Confirmed by Nandakumar, 02-Jul-26.
8 | MSE panel erection: 15 panels/day (P108 PRC-MSE) governs. P65 MSE-PAN 24/day and P1 20 m2/day superseded. | Resolved by Nandakumar, 02-Jul-26.
9 | P2 UT-* rows retained as relocation/protection-of-existing services, distinct from P1 new-works rates. | Confirmed by Nandakumar, 02-Jul-26.
10 | BG-UP Code Mapping sheet is DRAFT throughout; mappings by name similarity only, gaps marked GAP. | No invented rates. Confirmed to proceed as DRAFT, 02-Jul-26.
11 | Tool methodology (Rev 1): Duration (workdays) = Qty ÷ Rate/day at ONE crew. Any durations/finish dates in the input are overridden by Qty ÷ Rate. Crews are added later, manually, only if a duration must be compressed — user's call. | Per Nandakumar instruction, 02-Jul-26.
12 | Activities with no activity code in the input are ignored (counted, not flagged as issues). | Per Nandakumar instruction, 02-Jul-26.
13 | Default working calendar in the tool: 6 days/week Mon-Sat, 8 hrs/day (configurable per project). | House convention — confirmed as default, confirm per project.